## PFR Checklist
PROJECT FINANCIAL REPORT CHECKLIST (for RHO/CO internal use!) |  | Quarter | Year | Project # |  | Project Name, Country:
[9 empty] | Q1 | 2019 | x
QUESTIONS |  | YES | N/A | NO | COMMENTS (If 'NO': comment is mandatory!). Any comment provided must have the respective date!* |  | INPUT FROM | If 'NO' -Issue closed?** | Q2 | 2020
A. PFR General | [8 empty] | Q3 | 2021
1 | Has the partner used the right template as shared by RH/CO? i.e. ensure that the partner has not tampered with any unprotected information within the worksheets. | [5 empty] | Finance |  | Q4 | 2022
2 | Are all PFR header information correct and according to the current reporting period? (Most important to check : reporting period, currency, project duration ) | [5 empty] | Finance |  |  | 2023
3 | Was the PFR delivered on time? | [5 empty] | Finance
B. Project Budget vs Actual Expenditure
4 | Do the reported project expenditures look reasonable (compared with budget plan, expenses trends, previous reports and discussions, etc)? | [5 empty] | Finance
Programme
5 | Has the partner provided a comment for every budget line with a major 'balance at the project'? Are these comments well-justified and reasonable? | [5 empty] | Finance
Programme
6 | Is/are the surplus/es (positive 'Remaining MYP Budget' ) for every activity planned to be spent in the next quarter? (only applicable for PFR Q3 / RoF Q4) | [5 empty] | Finance
Programme
7 | Is the given 'Forecasted Expenditure (next quarter) ' reasonable (compared with budget plan, expenses trends, previous reports and discussions, etc)? (N/A for Q4 report) | [5 empty] | Finance
Programme
8 | Are all re-utilization of balances at the project according to CBMs Regulation for the re-utilisation of transferred funds well justified and reasonable? ("Partner has a 10% budget flexibility of transferred funds as long as funds are used within the same result, the result is maintained or improved through the re-utilisation and the total budget of the respective result is not overspent. All other re-utilizations need RHO/Initiative/PD approval beforehand") | [5 empty] | Finance
Programme
C. List of Expenditures (LoE)
9 | Does every reported expenditure / transaction look logical, realistic and credible? | [5 empty] | Finance
Programme
10 | Has the partner introduced all relevant data in the correct manner for each expenditure? << Minimum required data for a correct import: position/activity line n°, expenditure amount, currency code, date of expenditure (MM/DD/YY) >> | [5 empty] | Finance
11 | Is the given reporting currency (Overview header information, cell F4) correct? | [5 empty] | Finance
12 | Is the expenditure currency code for each expenditure entered (column D) in LoE and is it always the same code? | [5 empty] | Finance
13 | If the PFR is in hard currency (e.g. EUR) in LoE is the amount given in column K correctly calculated? | [5 empty] | Finance
14 | Do the expenditure totals per quarter (sum of column I) in LoE match with the total expenditure given in Overview (row 15, column C - H)? | [5 empty] | Finance
15 | Did you confirm the accurancy of position/activity numbers in the LoE against the budget? E.g. partner report expenditure for Result 01, but budget is on activity 02.01 - 05. | [5 empty] | Finance
16 | Do the expenditure dates match the respective reporting quarter? i.e. partner has not included expenditures from the prev. or the next quarters? | [5 empty] | Finance
17 | Has the partner maintained the expenditures in LoE from previous quarters unchanged? If changed, are the changes reasonable? (Not applicable for PFR Q1/RoF Q2) | [5 empty] | Finance
18 | If the partner is not supposed to report expenditure in details, but as a lump sum per budget line per quarter, is an information like "total expenditure for Q1" in the comment section entered? | [5 empty] | Finance
19 | If the partner is supposed to report expenditures in detail: are recipient of payment, invoice number and justification of payment correctly given? | [5 empty] | Finance
D. Transfer of Funds [CBM transfers]
20 | Have all transferred funds been acknowledged in the correct (expenditure) currency and with the correct (gross!) amount? | [5 empty] | Finance
21 | Can the PFR standard logic (quarterly average ex-rate) on how the ex-rate is calculated be applied for the project? | [5 empty] | Finance
22 | IF the PFR standard logic on how the ex-rate is calculated can not be applied, are the ex-rates adapted according to the individual agreed ex-rate? (e.g. for BMZ or other co-funded projects, ex-rate which has to be applied, is given from the resp. PD/Intiative) | [5 empty] | Finance
E. Actions to be taken at CBM (CO/RHO, IO,) level:
By whom? |  | What actions? |  |  |  |  | By when?
F. Actions CBM expects the partner to take at his level:
Who at CBM to initiate and monitor action? |  | What? |  |  |  |  | By when?
G. General comments/observations on the given PFR / Do you presume any risk at the project? | General comments/observations on the change report / Do you presume any risk at the project from the given PPR?:
Finance
Programme
H. Decision on the transfer
23 | Shall the transfer be arranged? (N/A for Q4 report) | [5 empty] | Finance
Programme
I. Processing and release of funds
24 | Are the RoF details, tcorrectly entered for the next RoF? (N/A for Q4 report) | [5 empty] | Finance
25 | Has the partner signed, scanned and shared the correct template? Please check that the details of the final agreed RoF are matching with the details of the signed RoF. | [5 empty] | Finance
26 | Is the signed RoF legible and in the right format (preferably in PDF) that is acceptable by CBM-IO Finance Department | [5 empty] | Finance
27 | Has the partner inserted the date and signed in the correct place? Is the signatory an authorized person as per the project contract? | [5 empty] | Finance
28 | Is the project (or any positions within the project budget) free of provisos? (to be checked in PROMiS) | [5 empty] | Finance
|  | Name & Title |  |  |  | Signature | Signature Date / Date of Confirmation
Checked by (Finance):
Checked by (Programm):
Approved by:
Orange marked Questions are "Completenes & Correctness" checks
Green marked Questions are "Qualitative" checks
* | Any comment provided in any section must have the respective date of when the comment was provided - purpose: tracking progress of the raised and closed issues
** | If the issue marked with "NO" was clarified and closed kindly enter the date and your respective name abbreviation in column J
KEY
CO - Country Office
IO - CBM International
PFR - Project Financial Report
RD - Regional Director
RHO - Regional Hub Office
RoF - Request of Funds
PD - Programme Delivery

## Sample
PROJECT FINANCIAL REPORT CHECKLIST (for RHO/CO internal use!) |  | Quarter | Year | Project # |  | Project Name, Country:
|  | Q2 | 2021 | P10192-MYP |  | Project for the implementation of a model of the integration of disabilityprevention and physical rehabilitation in the DRC National Health System, Republique Democratique du Congo |  |  | Q1 | 2019 | x
QUESTIONS |  | YES | N/A | NO | COMMENTS (If 'NO': comment is mandatory!). Any comment provided must have the respective date!* |  | INPUT FROM | If 'NO' -Issue closed?** | Q2 | 2020
A. PFR General | [8 empty] | Q3 | 2021
1 | Has the partner used the right template as shared by RH/CO? i.e. ensure that the partner has not tampered with any unprotected information within the worksheets. |  |  | x | Parnter initally used the old template |  | Finance |  | Q4 | 2022
2 | Are all PFR header information correct and according to the current reporting period? (Most important to check : reporting period, currency, project duration ) |  |  | x | Reporting periods were not entered correctlym(10.10.24) |  | Finance | Yes |  | 2023
3 | Was the PFR delivered on time? |  |  | x | PFR was deilivered 3 days late (01.10.24) |  | Finance | Yes
B. Project Budget vs Actual Expenditure
4 | Do the reported project expenditures look reasonable (compared with budget plan, expenses trends, previous reports and discussions, etc)? | x |  |  |  |  | Finance
Programme
5 | Has the partner provided a comment for every budget line with a major 'balance at the project'? Are these comments well-justified and reasonable? |  |  | x | The partner did not put comments on the Project Budget vs Exp sheet (01.10.24) |  | Finance | Yes
Programme
6 | Is/are the surplus/es (positive 'Remaining MYP Budget' ) for every activity planned to be spent in the next quarter? (only applicable for PFR Q3 / RoF Q4) |  |  | x | There is no information on whether the remaining funds were planned to be spent in the next quarter (01.10.24) |  | Finance
Programme
7 | Is the given 'Forecasted Expenditure (next quarter) ' reasonable (compared with budget plan, expenses trends, previous reports and discussions, etc)? (N/A for Q4 report) | x |  |  |  |  | Finance
Programme
8 | Are all re-utilization of balances at the project according to CBMs Regulation for the re-utilisation of transferred funds well justified and reasonable? ("Partner has a 10% budget flexibility of transferred funds as long as funds are used within the same result, the result is maintained or improved through the re-utilisation and the total budget of the respective result is not overspent. All other re-utilizations need RHO/Initiative/PD approval beforehand") | x |  |  |  |  | Finance
Programme
C. List of Expenditure (LoE)
9 | Does every reported expenditure / transaction look logical, realistic and credible? |  |  | x | Large expenditure, but lack of corresponding activities |  | Finance
Programme
10 | Has the partner introduced all relevant data in the correct manner for each expenditure? << Minimum required data for a correct import: position/activity line n°, expenditure amount, currency code, date of expenditure (MM/DD/YY) >> | x |  |  |  |  | Finance
11 | Is the given reporting currency (Overview header information, cell F4) correct? | x |  |  |  |  | Finance
12 | Is the expenditure currency code for each expenditure entered (column D) in LoE and is it always the same code? |  |  | x | Some currency codes were missing |  | Finance
13 | If the PFR is in hard currency (e.g. EUR) in LoE is the amount given in column K correctly calculated? | x |  |  |  |  | Finance
14 | Do the expenditure totals per quarter (sum of column I) in LoE match with the total expenditure given in Overview (row 15, column C - H)? | x |  |  |  |  | Finance
15 | Did you confirm the accurancy of position/activity numbers in the LoE against the budget? E.g. partner report expenditure for Result 01, but budget is on activity 02.01 - 05. |  |  | x | Partner sometimes uses the wrong code (10.10.24) |  | Finance
16 | Do the expenditure dates match the respective reporting quarter? i.e. partner has not included expenditures from the prev. or the next quarters? |  |  | x | No. some voucher dates were from the previous quarter (01.10.24) |  | Finance | Yes
17 | Has the partner maintained the expenditures in LoE from previous quarters unchanged? If changed, are the changes reasonable? (Not applicable for PFR Q1/RoF Q2) | x |  |  |  |  | Finance
18 | If the partner is not supposed to report expenditure in details, but as a lump sum per budget line per quarter, is an information like "total expenditure for Q1" in the comment section entered? |  |  | x | There is no comment provided (01.10.24) |  |  | Yes
19 | If the partner is supposed to report expenditures in detail: are recipient of payment, invoice number and justification of payment correctly given? | x |  |  |  |  | Finance
D. Transfer of Funds [cbm transfers]
20 | Have all transferred funds been acknowledged in the correct (expenditure) currency and with the correct (gross!) amount? | x |  |  |  |  | Finance
21 | Can the PFR standard logic (quarterly average ex-rate) on how the ex-rate is calculated be applied for the project? | x |  |  |  |  | Finance
22 | IF the PFR standard logic on how the ex-rate is calculated can not be applied, are the ex-rates adapted according to the individual agreed ex-rate? (e.g. for BMZ or other co-funded projects, ex-rate which has to be applied, is given from the resp. PD/Intiative) | x |  |  |  |  | Finance
E. Actions to be taken at CBM (CO/RHO, IO,) level:
By whom? |  | What? |  |  |  |  | By when?
PM - John Smith |  | Ensure partner does not submit late, send updated report with old duplicate vouchers removed. (10.10.24) |  |  |  |  | 01.11.24
F. Actions CBM expect the partner to take at his level:
Who at CBM to initiate and monitor action? |  | What Action? |  |  |  |  | By when?
PC - John Smith |  | Hold training session with key staff on how to complete PFRs in good quality |  |  |  |  | 15.10.24
G. General comments/observations on the given PFR / Do you presume any risk at the project? | General comments/observations on the change report / Do you presume any risk at the project from the given PPR?:
Mostly clerical issues and oversights. No expected additional risk identified | [6 empty] | Finance
Partner coding not always accurate. Causes delayes due to need for amendments. No additional risk in terms of time and scope but donor report may be in recorded incorrectly. | [6 empty] | Programme
H. Decision on the transfer
23 | Shall the transfer be arranged? (N/A for Q4 report) | x |  |  | Yes |  | Finance
[5 empty] | Yes |  | Programme
I. Processing and release of funds
24 | Are the RoF details, correctly entered for the next RoF? (N/A for Q4 report) | x |  |  |  |  | Finance
25 | Has the partner signed, scanned and shared the correct template? Please check that the details of the final agreed RoF are matching with the details of the signed RoF. |  |  | x | I do not see any signed documents |  | Finance | Yes
26 | Is the signed RoF legible and in the right format (preferably in PDF) that is acceptable by CBM-IO Finance Department |  | x |  | Because there is no signature |  | Finance
27 | Has the partner inserted the date and signed in the correct place? Is the signatory an authorized person as per the project contract? |  | x |  | Because there is no signature |  | Finance
28 | Is the project (or any positions within the project budget) free of provisos? (to be checked in PROMiS) |  | x |  |  |  | Finance
|  | Name & Title |  |  |  | Signature | Signature Date / Date of Confirmation
| Checked by (Finance): | Anabelle Fourcand (Project Finance Officer) |  |  |  | Afourcand | 2024-07-10
| Checked by (Programm): | Peter Shilling (PO) |  |  |  | Peter S | 2024-10-07
| Approved by: | Shirlie Owens (PM) |  |  |  | Shirlie O. | 2024-07-10
Orange marked Questions are "Completenes & Correctness" checks
Green marked Questions are "Qualitative" checks
* | Any comment provided in any section must have the respective date of when the comment was provided - purpose: tracking progress of the raised and closed issues
** | If the issue marked with "NO" was clarified and closed kindly enter the date and your respective name abbreviation in column J
KEY
CO - Country Office
IO - CBM International
PFR - Project Financial Report
RD - Regional Director
RHO - Regional Hub Office
RoF - Request of Funds
PD - Programme Delivery