**QRT 1 & 2-CBID ACTIVITY HIGHLIGHTS**

|  |  |  |  |
| --- | --- | --- | --- |
| Activity Code | Activity Name | Achievements | No of Beneficiaries |
| 01.01.01 | Health Promotion: Conduct 18 community awareness events in Lusaka, Luapula, Muchinga and Northern Provinces. | **QRT 1**  Working with ministry of health, physiotherapy department. Two awareness events conducted in Samfya and Mwense district | * Targeted beneficiaries during the awareness events conducted comprised of care-givers of children with disabilities and traditional leaders. * 34 attended the awareness meeting in Samfya and 29 in Mwense district. * Physiotherapists raised on awareness on the services provided and encouraged care-givers of children with CP to take their children for physical therapy |
|  |  | **QRT 2**  Four awareness meetings conducted during the parent support group meetings from four different communities of Lusaka namely; Kanyama, Kasupe, Kahale village and Twatasha OVC in Kafue  **Key messages disseminated to caregivers of children with CP**   * Services provided at BCH for children with CP highlighted by the physiotherapist * Physical therapy * Provision of assertive devices * Need to strengthened community based support groups | Total number of care-givers reached:   * Kanyama- 6 mothers and 1 father * Kahale Village-8 mothers * Kasupe- 9mothers and 1 father * Kafue- 19mothers and 2 fathers |
| 01.01.02 | Promotional Materials | **QRT 1**  Over a 100 awareness brochures distributed during the ENT world hearing day commemorations  **QRT2-** Over 100 Flyers with |  |
|  |  | information on the conditions treated at BCH distributed in 4 communities during the parent support group meetings and wheelchair follow-ups |  |
| 01.01.03 | Conduct 10 media shows covering Lusaka, Luapula, Muchinga and Northern Province | **QRT1**   * 1 media show   conducted in Chongwe district   * 2 Care-givers of children with CP participated on the radio shows and encouraged other caregivers to form and join support groups |  |
|  |  | **QRT2**  1 TV live show conducted on ZNBC raising awareness on clubfoot and the importance of accessing early treatment in children to prevent permanent disability |  |
| Activity 03.04 | Form 03 parent support groups of 30 members each in Lusaka | **QRT2**  Following a successful training held in first quarter on basic CP management for caregivers of children with CP.  Four new community based support groups have been formed in Kanyama compound, Kasupe, Kahale village and Twatasha OVC in Kafue.   * Community based parent support groups are aimed at promoting and strengthening community based rehabilitation among care-givers of children with disabilities.   During the parent support group meetings, two physiotherapist present during the 4 meetings conducted encouraged care-givers to identify more parents of children with disabilities to join the support groups in order to promote inclusive development for children with disabilities. Other issues highlighted during the meetings include; the importance of play therapy, nutrition, feeding and positioning.  The orientation meetings will be followed up by detailed sessions on the topics highlighted | Total number of care-givers present during the parent support group meetings:   * Kanyama- 6 mothers and 1 father * Kahale Village-8 mothers * Kasupe- 9mothers and 1 father * Kafue- 19mothers and 2 fathers |
| 04.01 | Conduct training for 30 support groups’ members in community mobilization and social auditing skills. | **QRT1**   * With support from creative women of the world,(CWOW) 38 women from Chongwe districts have been trained in business management skills. Enhancing their knowledge and capacity to grow their businesses by providing them business opportunities to supply different types of products like pillow cases and table runners to the US. * The women groups from Lusaka and Chongwe have since supplied a total of 10 table runners and 30 pillow cover to CWOW-US.   CWOW has leveraged on the already existing structures following the successful CBID empowerment program implementation |  |