**Quarterly Narrative Report (QNR)**

(Please complete the following report within 30 days after every quarter. Max 6 pages)

|  |  |  |  |
| --- | --- | --- | --- |
| Project Implementing Partner: | **Nepal Netra Jyoti Sangh (NNJS)/ Eastern Region Eye Care Program (EREC-P)** | | |
| **Project Name:** | **Sundar Sansar (Beautiful world):** **Reduce Visual and Hearing Impairment among School going children in Nepal** | | |
| **Project no:** | P00124 | | |
| **Project Reporting Period** | **July 18, 2022** | | |
| **Project Start Date:** | **April 2022** | Project End Date: | **DEC 2023** |
| **Total Project Budget :** | **EUR-1,00,000** | Report Date Submission: | **July 18, 2022** |
| **Report Author:** | **Sanjay Yadav, Program Supervisor** | | |
| **CBM Global Country Team Project Manager** | **Bikash Pyakurel** | | |

This report is intended to be submitted quarterly but reflect the entire project period to date. It should be an accurate description of project progress and the content of the final version to be agreed between the implementing partner and the CBM Global Country Team before being uploaded to Global Online.

**CBM Global Checklist**

**Please ensure the following documents are up to date:**

|  |  |
| --- | --- |
| **Activity Plan** |  |
| **Indicator Tracker** |  |
| **Risk Register (every six months)** |  |
| **Monitoring and Evaluation Plan (every six months)** |  |

**When compiling this report, complete in the following order: 1) Update activity plan, 2) record progress against indicators in log frame, 3) update risk register (every 6 months) and 4) update M&E plan. 5) After updating these documents complete the narrative report below.**

|  |
| --- |
| 1. Summary of project progress during the quarter. Put an ‘X’ on the RAG scale (red - critical, amber - moderate, green- good) to reflect project progress. Rate and justify your rating in 2-3 sentences maximum. |
| We are going to start school screening program from end of July. So, we can report about the progress of the project from coming 3rd quarter. We have just prepared to enter in the phase of program intervention. We have gone through the process of hiring staffs and selection of staffs for the project have been completed. Different forms and formats for the projects have been developed and printed. Coordination and approval from different local unit of Morang have been completed.  Since the project isn’t started smoothly, no any key issues have arisen which are to be addresses or discussed. Since the project starts from June,2022, there is no any monitoring visits have been done.   |  |  |  |  | | --- | --- | --- | --- | | **Project Progress** | Critical | Moderate X | Good | |
| **2. Comment on project progress against project targets and indicators.** In addition, give details of targets and indicators which are currently off track according to the log frame and note remedial actions planned or taken. |
| Moderate:  We are going to start school screening program from end of July. So, we can report about the progress of the project from coming 3rd quarter. We have just prepared to enter in the phase of program intervention. We have gone through the process of hiring staffs and selection of staffs for the project have been completed. Different forms and formats for the projects have been developed and printed. Coordination and approval from different local unit of Morang have been completed. |
| 3. Project progress against the project activity plan: Please comment on and highlight activities (by indicating activity numbers) which are behind schedule and where changes are needed. Give reasons and justifications for any delay and further proposed changes to the activity plan. Assure that the activity plan is updated accordingly and attached to this report. |
|  |
| **4. Budget implementation/significant budget variances.** Please comment on budget implementation and any budget variances which deviate from the budget plan (greater than 10% cumulative year to date at result level, unless otherwise stated by specific funder requirements). |
| **N/A** |
| **5. Key issues that have arisen or need to be addressed or discussed.** Please use this space to comment on any other challenges that have arisen during the reporting period which are not captured by the above questions. |
| Since the project isn’t started smoothly, no any key issues have arisen which are to be addresses or discussed. During next quarter it will be reported as the project progress lead ahead and if any issues will arises. |
| **6. Monitoring Visits, Actions, and Recommendations.** If a monitoring visit/call was conducted during the quarter, please copy and paste a link to the relevant project monitoring visit/remote monitoring call report in GO which mentions the main findings and recommendations following the completion of the visit/call. |
| * Since the project starts from June,2022, there is no any monitoring visits have been done. |